## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/14-09/28 | Finalised a project idea. Learned about some github features. Decided the roles of each member Discussed the configuration and QA plan. Finalized the tech stack. Analyzed the risks of the project. Analyzed performance metrics for the project. Worked on the documentation. Worked on the presentation for iteration 0. | Members faced few issues on the implementation of Lab1. Sought assistance from teammates. Members are not familiar with certain frameworks. | Faced issues with deciding on the weekly meeting schedule. | - Discussed the project idea with Professor. Added a few functionalities to our project based on Professor's suggestions. - Switched from JIRA to Pivotal Tracker. - Decided to change our branching strategy from Git Flow to GitHub flow branching strategy. | [5 empty] | 24 | 21 | 3
1 | 09/29-10/19 | Completed automated tools configuration. Worked on YouTube API integration with the application. Constructed low-fidelity wireframes. Worked on more user stories. Worked on design patterns, class diagram, database diagram, etc. Worked on the presentation and demo for Iteration 1. Worked on the documentation. | 1. Issues faced with github action tools, several tools were incompatible, or required a paid subscription 2. Faced issues while configurating codeql with python as a sample python code was needed to complete it. | Faced issues with the distribution of work. | -Decided on the flow of work for the next iterations. -Made changes in the class diagram. | 5 | 4 |  |  |  | 111.5 | 108.5 | 3
2 | 10/20-11/09 | Assigned work based on user stories. Individually worked on coding. Made branch for each user story with their respective numbers and titles. Created pull requests for each component. Reviewed pull requests and requested changes if needed. Merged all the pull requests once they were reviewed and fulfilled as per requirement. Worked on the presentation and demo. Worked on the Documentation | 1. Issues faced in pushing the code to github by few members. |  | -Discussed about our individual work and if any problems faced in achieving them. -Discussed on the work for next slot of user stories to be worked on. | [5 empty] | 145 | 140 | 5

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Siddhesh
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 7 | 6 | 1 | 5 - helping team members to onboard to git repository and help with their git repo setup, Communicating with team to find common time to schedule weekly meeting 6 - git repository creation, set up git repo locallly 7 - think and discuss project ideas | [5 empty] | 2 | 1 | 3 | 1. set up git 2. finalized tech stack to be used for the project |  | 1 - Finalise a project idea. 2 - work on SPPP 3 - Work on Presentation for iteration 0 | 1. Finish all the required documentations for Iteration 0 | 6
2 | 09/21-09/28 | 10 | 8 | 2 | 0 - learn about YouTube API, Integration of firebase with Python Flask 5 - deciding performance metrics, functional and non functional requirements & disscussing tools to use for CI/CD and Testing, Preparing presentation & SPPP Document with teammates for Iteration 0 | 3 |  |  |  |  | 5 |  |  | 1. started working on creating features/tasks to be made into JIRA tickets | 1. Not very familiar with integration between Flask and Firebase | 1. Learning about YouTube API and exploring its features by creating a dummy application 2. Learning about Firebase integration with Flask by creating a dummy application 3. Learn more about code review techniques and quality assurance metrics | 1. Write initial feature stories and find time to connect with team to groom feature stories and acceptance criteria 2. Work on initial wireframes / mockups with team members for core functionalities and screens 3. Setup a call with team members for teaching basics of React | 7
3 | 09/29-10/05 | 8 | 5 | 3 | 0 - learn about YouTube API 2 - working on creating low fidelity wireframes | 3 |  | 2 | [5 empty] | 1. Tested all the features to be used through YouTube API 2.Prepared wireframes to make creating detailed user stories easier |  | 1. Start working on creating detailed user stories for the functionality of the app 2. Work on setting up the intial project structure |  | 7
4 | 10/06-10/12 | 8 | 5 | 3 | 3. Initial project setup 4. Integration with CyPress for testing |  |  |  | 2 | 3 |  |  |  | 1. Created initial project structure to be used for the project 2. Integrated Cypress for writing UI and API test cases |  | 1. Start with designing initial pages with hardcoded values 2. Finish integrating Youtube api to enable search functionality through the app |  | 7
5 | 10/13-10/19 | 12 | 8 | 4 | 3. Designing Homepage and writing test cases for it 3. Designing search page with its test cases 3. Integrated Yoube API to fetch videos 7. Created presenstation for Iteration 1 |  |  |  | 7 |  |  |  | 1 | 3. Worked on designing and testing multiple pages for the project 4. Implmented configuration logic for integrating YouTube API to the project | 1. Faced issues when trying to query YouTube directly through flask | 1. Work on increasing the number of videos fetected through the app 2. Work on the video watching page 3. Work on capturing user's watching time and other meta data to gain insight on user's experience | 1. Design and write logic for the "Video watching" page where the user can play the video 2. Setup database and finalise database design to store user's watch history | 10
6 | 10/20-10/26 | 10 | 7 | 3 | 0 - Learn about YouTube Player API for tracking users watch time 5 - Conducted a session on react for the entire team 7 - Worked on migrating Youtube API call from front-end to back-end 7 - Designed Browsefeed section sperating YouTube videos in 3 sections as per duration | 1 |  |  |  | 2 |  |  | 4 | 1. Worked on migrating Youtube API call from front-end to back-end 2. Designing Browse Feed section for different video duration
7 | 10/27-11/02 | 9 | 7 | 2 | 5 - Conducted a session on cypress testcases 7 - Integrating YouTube player api with the code 7 - Tweaking YouTube API python api to support parameters requests with query, duration and total video count being passed as parameter 5 - Code reviewing teams pull requests | [5 empty] | 4 |  | 3 | 1. Refactoring YouTube API call into a single flask parameterized route to avoid duplicated code 2. Migrated from <iframe> to YouTube API Player which provides a more granular control over users action while watching videos | 1. npm issues while running teams changes locally for code review 2. multiple merge conflicts while dealing with merging teams code on git
8 | 11/03-11/09 | 15 | 11 | 4 | 7 - Integrating firestore database with the code 7 - Writing api's to add user details from user's google profile to firestore 7 - Writing api to read data from firestore to fetch users hobbies 7 - Integrating teams changes to the app 7 - Designing onboarding, see all videos and Youtube watch experience page 5 - Code review for teams changes 5 - Help team solve merge conflicts and other git related issues while merging | [5 empty] | 5 |  | 6 | 1. Integrated teams changes into the main app 2. Designed onboarding, see all videos and Youtube watch experience page 3. Integrated firestore and implemented read and write routes to update firestore | 1. Cypress test cases failing due to the login requirement 2. YouTube API exhausting total daily quota | 1. Started working on creating a spooler to pick different Youtube when one api is exhausted 2. Added failback to default user for cypress to work without login | 1. Write logic to write video related meta data to database and capture watch time 2. research for different web chart libraries to display analytics | 10

## Sai Ramya
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project. |  | 1. Finalise a project idea. 2. work on risk mgmt doc
2 | 09/21-09/28 | 5 | 3 | 2 | 0 - learn github functions, brushing up Flask concepts 7 - Analyzed the risks for iteration 0 | 2 | [6 empty] | 1 | 1. completed the risk management document for the iteration 0
3 | 09/29-10/05 | 6 | 3 | 3 | 2 - discussing and creating user stories |  |  | 3
4 | 10/06-10/12 | 6 | 5 | 3 | 0 - learn flask 2 - drafted low level wireframes | 3 |  | 2 | [5 empty] | 1. Help with the low level wireframes for further user stories
5 | 10/13-10/19 | 6 | 4 | 4 | 0 - learn react, brush up flask 5 - discuss low wireframes | 2 |  |  |  |  | 3 |  |  | 1. Worked on the SDDD , database design
6 | 10/20-10/26 | 7 | 5 | 2 | 0 - learn react, understand the already existing code that has been built and try building reusable components. | 5 | [7 empty] | 1. Started implementing the Jira assigned to me SE-29
7 | 10/27-11/02 | 4 | 3 | 1 | 3 - trying implementation of reusable components to display on see more button from the education page |  |  |  | 3
8 | 11/03-11/11 | 17 | 11 | 6 | 3 - Implement the landing page for the see more videos. 7- Faced issues and pair programmed with siddhesh and deepali for PR's and issues within the assigned tasks. Worked on documentation for the project. |  |  |  | 11 |  |  |  | 6 | 1. submitted PR for changes. 2. Worked on SDDD changes requested by Prof. after Iteration1. 3. Worked on STD documentation. | Issues faced with react, was facing difficulty in fetching states

## Supriya
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project.
2 | 09/21-09/28 | 4 | 2 | 2 | 0 - learn github functions,commands, learn Flask concepts,discussion with team lead regarding project learn deployment for flask and react | 2 | [7 empty] | 1. completed the document for the iteration 0
3 | 09/29-10/05 | 6 | 3 | 3 | 2. Discussing User Stories. |  |  | 2
4 | 10/06-10/12 | 12 | 8 | 3 | 0. Acquring proficiency in github actions Learn JIRA LEARN FLASK | 5 | [5 empty] | 3 |  | 1.assistance with low level wireframes for use cases
5 | 10/13-10/19 | 6 | 5 | 2 | 0.Gaining proficiency in GitHub tools and Flask 2. worked on user stories | 4 |  | 1
6 | 10/20-10/26 | 7 | 5 | 2 | 0.Understand how to use React and comprehend the built-in code currently there. | 6 | [7 empty] | began working on the Jira that was assigned to me, SE-34.
7 | 10/27-11/02 | 7 | 6 | 1 | 3. composed and created the user profile page's code 0.Learn the fundamentals of React and the current codeflow. | 1 |  |  | 5 |  |  |  |  | began working on the Jira that was assigned to me, SE-35.
8 | 11/03-11/09 | 19 | 17 | 2 | 3. Composed code to generate a webpage for viewing video history. 0.Engaged in learning React components and familiarizing o with Git commands 7.encountered problems and worked with Deepali to solve problems and PRs related to the tasks given. worked on the project's documentation. | 14 | [6 empty] | 3 | submitted PR for changes for SE-34 and SE-35

## Paridhi
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirements leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project.
2 | 09/21-09/28 | 9 | 7 | 2 | 0 - learn GitHub features and functionalities such as Github Desktop, brush on Flask and React, and learn about JIRA and Cypress. 5 - had meetings and worked on the progress report. | 4 |  |  |  |  | 3 |  |  | 1. completed the group progress report.
3 | 09/28-10/06 | 7 | 4 | 3 | 2 - Created user stories |  | 4
4 | 10/06-10/13 | 10 | 7 | 3 | 0 - learn Flask and React, and learn about JIRA and Cypress. 2 - edited and manually added user stories. | 5 | 2 | [6 empty] | 1. Completed editing and updating the user stories imported from pivotal tracker.
5 | 10/13-10/19 | 12 | 8 | 4 | 2 - created more user stories based on the wireframes. 5 - attended meetings and worked on documentation. Discussed the wireframes construction and gave suggestions. |  | 4 |  |  |  | 4 |  |  | 1. Completed working on the user stories. 2. Completed documentation. | Faced issues in exporting user stories in bulk from JIRA to Github and Drive.
6 | 10/20-10/26 | 4 | 2 | 2 | 0 - learn React and understand the basic structure of the existing code. | 2
7 | 10/27-11/02 | 4 | 3 | 1 | 0 - learn React and how to build the watch page. 2 - updated Jira stories as we started working on it. | 2 | 1
8 | 11/03-11/09 | 13 | 11 | 2 | 0 - learn about the TDD technique. 2 - updated Jira stories progress. 3 - started working on the implementation of watch page. 5 - faced issues in making pull requests, took help from team members. | 1 |  | 1 | 7 |  | 2 |  |  | 1. Completed implementation of the watch page. 2. Completed documentation. | 1. Faced issues in making pull requests and updating the final code(integration). 2. Faced issues in creating the watch page and usage of APIs. | 1. Took help from teammates for the github issues. 2. Referred to youtube videos to learn about the watch page and API usage.

## Deepali
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project. |  | 1. Finalise a project idea. 2. work on SPPP
2 | 09/21-09/28 | 10 | 8 | 2 | 0 - learn github actions, deployment for flask and react, docker containerisation 5 - decided on and discussed configuration plan and QA plan with team members 6 - came up with a configuration plan | 5 |  |  |  |  | 2 | 1 |  | 1. started process of configuration of CI/CD tools using github actions | 1. Not familiar with react 2. Not familiar with QA processes | 1. took help from team member for React. 2. learning more about QA metrics and testing. 3. plan: complete CI/CD configuration and try it out on a dummy application
3 | 09/29-10/05 | 7 | 4 | 3 | 2 - discussing and creating user stories |  |  | 4
4 | 10/06-10/12 | 12 | 9 | 3 | 0 - learn github actions 6 - tested configurations for different pre-existing action tools, imported user stories from pivotal tracker to JIRA, set up JIRA | 4 | [5 empty] | 5 |  | 1. set up the JIRA project, started sprint 2. tried out configuring automated tools on dummy app
5 | 10/13-10/19 | 14.5 | 10.5 | 4 | 0 - learn react, brush up flask 4 - tested configurations on project github repo - resolve errors 5 - discuss lofi wireframes | 3 |  |  |  | 7 | 0.5 |  |  | 1. set up github action tools on repo | 1. Issues faced with github action tools, several tools were incompatible, or required a paid subscription | 1. referred to documentations and resources online
6 | 10/20-10/26 | 7 | 5 | 2 | 0 - learn react, understand how it will be used in our project through Siddhesh's demo. 5 - prepare documentation for team members for github usage, PR standards etc. 6 - look at deployment options for the project | 3 |  |  |  |  | 1 | 1 |  | 1. documentation for git usage
7 | 10/27-11/02 | 4 | 3 | 1 | 0 - try basic react and understand existing codeflow | 3
8 | 11/03-11/09 | 19 | 18 | 1 | 0 - get familiarised with cypress 3 - Implement the landing page for the entertainment feed. 5 - helped teammates with git issues, reviewed PRs, and merged and tested code. | 1 |  |  | 10 |  | 7 |  |  | 1. submitted PR for changes | Issues faced with react, was stuck at component usage within loops

## Ayush
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project.
2 | 09/21-09/28 | 6 | 4 | 2 | 0 - Discover the various features and functionalities of GitHub including GitHub Desktop, Issues, and Pull Requests. 5 - Had group meetings and worked on the progress report and other documentation for Iteration 0. | 3 |  |  |  |  | 1 |  |  | 1. Discussed and worked on progress report.
3 | 09/29-10/05 | 5 | 3 | 2 | 2 - Discussed and create user stories |  |  | 3
4 | 10/06-10/13 | 5 | 2 | 3 | 0 - learn JIRA and flask 6 - tested configurations for different action tools | 1 | [5 empty] | 1 |  | 1.Worked on tasks from pivotal tracker
5 | 10/13-10/19 | 6 | 4 | 2 | 0- Learn flask and user stories 5 -Worked on progress report documentation. 6-Discussed and worked on abuse on use case for project | 1 |  |  |  |  | 1 | 2
6 | 10/20-10/26 | 4 | 2 | 2 | 0- Learn flask and react 5- talked about the different wireframes that will be needed | 1 |  |  |  |  | 1 |  |  | 1. Worked on progress report and final documentation.
7 | 10/27-11/02 | 4 | 3 | 1 | 1- learn about react and our codeflow 2- designed a wireframe for the onboarding page | 1 | 2 | [6 empty] | 1. Started with the tasked assigned in JIRA SE-38
8 | 11/03-11/10 | 12 | 8 | 4 | 0- learn react and its libraries 3- Implemented the onboarding page and also linked it with signup page with the help of pushkar. 5- discuss about issues to add code in git and also learn about JIRA user stories | 1 |  | 5 |  |  | 2 |  |  | 1. submitted PR for changes and made changes as asked. 2. Worked on progress report | Issues faced in git PR was not able to connect code with git and issues with fetching code.

## Pushkar
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - Learn git commands and usage 6 - Set up git 7 - Discussed project ideas | 1 | [5 empty] | 1 | 2 | 1. Set up git 2. Shortlisted a few git tools and commands that would be useful for the project. |  |  | 1. Finish all the required documentations for Iteration 0 | 4
2 | 09/21-09/28 | 6 | 4 | 2 | 0 - Configured github. 5 - Had meetings and worked on the progress report. | 1 |  |  |  |  | 3 |  |  | 1. Worked on the groupreport and risk management report. |  |  | 1. Start implementing and work on basic of react. | 6
3 | 09/28-10/06 | 6 | 4 | 2 | 0- learn Pivotal tracker | 4 | [7 empty] | 1. Completed editing and updating the user stories imported from pivotal tracker.
4 | 10/06-10/13 | 5 | 2 | 3 | 4 - Examined the risks of project. 0- Learn flask and user stories 5 -Worked on risk management documentation. 6-Discussed and worked on abuse on use case for project |  |  | 2 | [5 empty] | 1. Completed the Designs patterns in SDD
5 | 10/13-10/19 | 6 | 5 | 1 | 2.Researched and designed the Design pattern. 3.Made the necessary adjustments in the risk management and carried out the required trials |  |  | 2 | 3 |  |  |  |  | 1. Work on the user stories was finished. 2. Finalized the documentation.
6 | 10/20-10/26 | 7 | 5 | 2 | 0 - learn react, followed project through Siddhesh's demo. 0 - learned from Deepali's documentation about github usage, PR standards etc. 1 - Started to research about authenticaiton system and Sign In functionality. | 3 | 2 | [6 empty] | 1. Started the implementing the Jira SE-25
7 | 10/27-11/02 | 4 | 3 | 1 | 3 - Completed the Jira SE-25 |  |  |  | 3 |  |  |  |  | 1. Solved the errors that occured during merging the code with the help of my fellow teammates | 1. Encountered some issues in the code while merging
8 | 11/03-11/09 | 10 | 6 | 4 | 0 - learnt more functionalities of Github 1 - Started to study about the Jira SE-32 3 - Helped Ayush with Onboarding page | 1 | 1 |  | 4 |  |  |  |  | 1. submitted PR for changes.