## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/14-09/28 | Finalised a project idea. Learned about some github features. Decided the roles of each member Discussed the configuration and QA plan. Finalized the tech stack. Analyzed the risks of the project. Analyzed performance metrics for the project. Worked on the documentation. Worked on the presentation for iteration 0. | Members faced few issues on the implementation of Lab1. Sought assistance from teammates. Members are not familiar with certain frameworks. | Faced issues with deciding on the weekly meeting schedule. | - Discussed the project idea with Professor. Added a few functionalities to our project based on Professor's suggestions. - Switched from JIRA to Pivotal Tracker. - Decided to change our branching strategy from Git Flow to GitHub flow branching strategy. | [5 empty] | 24 | 21 | 3
1 | 09/29-10/19 | Completed automated tools configuration. Worked on YouTube API integration with the application. Constructed low-fidelity wireframes. Worked on more user stories. Worked on design patterns, class diagram, database diagram, etc. Worked on the presentation and demo for Iteration 1. Worked on the documentation. | 1. Issues faced with github action tools, several tools were incompatible, or required a paid subscription 2. Faced issues while configurating codeql with python as a sample python code was needed to complete it. | Faced issues with the distribution of work. | -Decided on the flow of work for the next iterations. -Made changes in the class diagram. | 5 | 4 |  |  |  | 111.5 | 108.5 | 3
2 | 10/20-11/09 | Assigned work based on user stories. Individually worked on coding. Made branch for each user story with their respective numbers and titles. Created pull requests for each component. Reviewed pull requests and requested changes if needed. Merged all the pull requests once they were reviewed and fulfilled as per requirement. Worked on the presentation and demo. Worked on the Documentation | 1. Issues faced in pushing the code to github by few members. |  | -Discussed about our individual work and if any problems faced in achieving them. -Discussed on the work for next slot of user stories to be worked on. | [5 empty] | 145 | 140 | 5
3 | 11/10 - 12/10 | Assigned work to everyone and did peer pairing. Made branches for each each user stories and numbered and titlesd them according to JIRA. Created pull reuests and reviewed PRs of others. Did polishing on the design of all the webpages. Worked on both API and UI testing. Solved all the pending issues mentioned on github and merge conflicts. Merged all the code to the main. Worked on the presentation and demo. Worked on the documentation. | 1.Faced issues in testing 2.Faced issues in merging all the codes. | Everyone worked on their own pace which lead to a lot of last minute work. | -Worked together by sitting in the library and resolving all the doubts and issues together. -Completed all the project work on time with the given suggestions from the professor. | [5 empty] | 227 | 204 | 23

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Deepali Chawla | Management Plan (Objective) Configuration management plan Coding Standard Testing code review process defect management | Added few user stories, shifted from pivotaltracker to jira, added sprints | Class Diagram Design pattern Database design | Testing summary Cypress testing - screenshots | Presented in iterations 0, 1, 2, 3 | - Git Actions - Entertainment feed - Reward Points - unittests for backend - cypress tests (entertainment feed) - refactoring - bug fixes | unittest for python (backend) Added cypress tests | Git actions - codeQL (python and JS) - github action tester - dependency review | - Took a session on github - Coordinated with team to merge PRs - helped with github commits, rebasing and merge conflicts - tracked meeting minutes a few times - found some bugs and reverted incorrect code from main | - learnt how react works - learnt how github actions work - learnt about cypress testing (UI) - learnt about youtube data API - learnt Youtube player api
Pushkar Gharat | Team members | Added few user stories, Updated user points | Design Patterns |  |  | - Integrating Firebase - Google Sign-in Functionality - Session Timer - Reward Points - VideoDetails design update - VideoCard design update - OnboardingPage design update - Landing page(App.css) design update - update userprofile design - Update design of Search page - API Test to get user hobbies - API test to fetch videos | - API Test to get user hobbies - API test to fetch videos | Helped Configuration leader in reviewing and merging PRs. | Tracked weekly meeting minutes and did peer programing on watch timer and reward points. | - Learning how react works - Learning how Jira works - Learning how GitHub works - Learning how to do cypress testing - Learning how YouTube API works - Learning about ApexCharts - Learning about how to track watch time with YouTube Player API
Siddhesh Dighe | Overview Related Work Proposed High Level Requirements - Functional Requirements Proposed High Level Requirements - Nonfunctional Requirements Quality Assurance Plan | Created initial user stories list to be imported to jira | - Introduction - Software Architecture - UI Design | - Manual Testing Report | - Created Presentations for Iteration 0, 1, 2 - Presented in Iteration 0, 1, 2, 3 | - Setting up initial project - Integrating Cypress, Apex Charts, Firebase - Implementing YouTube API fetch to get data as per keyword - Implementing Tracking user watchtime - Implementing Charts | - Initial cypress setup for writing test cases - Added UI test cases for the search page, landing page and browse feed page | Helped Configuration leader in reviewing and merging PRs. Assisted the Configuration leader by reviewing and merging pull requests (PRs). | - Took a session on React for the entire team - Coordinated with team to get tasks done - Tracked meeting minutes a few times - Tracking tasks progress weekly | - Learning how YouTube API works - Learning about ApexCharts - Learning about how to track watch time with YouTube Player API
Sai Ramya Devineni | Management Plan Requirements | Added user stories to pivotal tracker and jira | Database Design MVC Component Architecture | Manual Testing Report Automated Testing Report | Created slides for Presentation in Iteration 3 | See All Videos Page Video Experience Buttons Reverted bad codes Connected Backend to python (app.py) to fetch videoDetails Refactored EntertainmentFeed.js Solved Github bugs and pushed the fixed code | Worked on unit tests for Wrapper Worked on Cypress tests for Navigates and buttons in Front end | Helped other team members merge and create PR Assisted Configuration Leader wherever needed | Handled meeting minutes Led meeting in absence of Team Leader | Learned how YouTube API works Learned React Learned Flask Learned how to do testing (unit tests) Learned how to do testing (cypress tests) Learned Firebase Learned GIT actions , how to resolve conflicts , how to merge , pull extra
Paridhi Talwar | Changed Estimated hours | Added new user stories Updated previous user stories Updated user points |  | Worked on cypress test Added screenshots for the same | Created slides for iteration 3 Presented in Iteration 0, 1, 2,3 | Worked on Video Details component Worked on reward points deduction feature. | Worked on Cypress API testcase for different features Worked on Cypress UI tests for different pages. | Helped Configuration leader in reviewing and merging PRs. | Tracked weekly meeting minutes | Learning on how Youtube API works Learning react and flask Leanrning how JIRA works Learning on how to write cypress test for both API and UI Learning on how to reduce or deduct points using API
Supriya Uppala | Track on riskmanagement document | Added user stories to pivotal tracker and jira |  |  | Created slides for iteration 3 Presented in Iteration 0, 1, 2,3 | worked on User Profile page worked on Video History page | Worked on Cypress UI tests for different pages. | Assisted the Configuration leader by reviewing and merging pull requests (PRs). | Tracked weekly meeting minutes | Learning React and Flask Learning how JIRA works Learning how Youtube API works Learning how to write Cypress tests
Ayush Bhaliya | Proposed security use case diagram | Active User Checker Login Page |  | Worked on watch history cypress api testing | Created slides in iteration 2 and 3 and also presented in iteration 2 and 3 | - Onboarding page - Google Sign-in Functionality - Session Timer - Reward Points - videogridcontainer design change - Videohistory design change - Userprofile page updated - userprofile design pdated - watchhistoryvideo api test | Worked on watch history cypress api testing | Helped team leader in reviewing and merging PRs. | Tracked weekly meeting minutes and did peer programing on watch timer and reward points. | - learnt how react works - learnt about cypress API testing - Learning how JIRA works and worked on task of jira -Learning how github works and it pull and push functions

## Siddhesh
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 7 | 6 | 1 | 5 - helping team members to onboard to git repository and help with their git repo setup, Communicating with team to find common time to schedule weekly meeting 6 - git repository creation, set up git repo locallly 7 - think and discuss project ideas | [5 empty] | 2 | 1 | 3 | 1. set up git 2. finalized tech stack to be used for the project |  | 1 - Finalise a project idea. 2 - work on SPPP 3 - Work on Presentation for iteration 0 | 1. Finish all the required documentations for Iteration 0 | 6
2 | 09/21-09/28 | 10 | 8 | 2 | 0 - learn about YouTube API, Integration of firebase with Python Flask 5 - deciding performance metrics, functional and non functional requirements & disscussing tools to use for CI/CD and Testing, Preparing presentation & SPPP Document with teammates for Iteration 0 | 3 |  |  |  |  | 5 |  |  | 1. started working on creating features/tasks to be made into JIRA tickets | 1. Not very familiar with integration between Flask and Firebase | 1. Learning about YouTube API and exploring its features by creating a dummy application 2. Learning about Firebase integration with Flask by creating a dummy application 3. Learn more about code review techniques and quality assurance metrics | 1. Write initial feature stories and find time to connect with team to groom feature stories and acceptance criteria 2. Work on initial wireframes / mockups with team members for core functionalities and screens 3. Setup a call with team members for teaching basics of React | 7
3 | 09/29-10/05 | 8 | 5 | 3 | 0 - learn about YouTube API 2 - working on creating low fidelity wireframes | 3 |  | 2 | [5 empty] | 1. Tested all the features to be used through YouTube API 2.Prepared wireframes to make creating detailed user stories easier |  | 1. Start working on creating detailed user stories for the functionality of the app 2. Work on setting up the intial project structure |  | 7
4 | 10/06-10/12 | 8 | 5 | 3 | 3. Initial project setup 4. Integration with CyPress for testing |  |  |  | 2 | 3 |  |  |  | 1. Created initial project structure to be used for the project 2. Integrated Cypress for writing UI and API test cases |  | 1. Start with designing initial pages with hardcoded values 2. Finish integrating Youtube api to enable search functionality through the app |  | 7
5 | 10/13-10/19 | 12 | 8 | 4 | 3. Designing Homepage and writing test cases for it 3. Designing search page with its test cases 3. Integrated Yoube API to fetch videos 7. Created presenstation for Iteration 1 |  |  |  | 7 |  |  |  | 1 | 3. Worked on designing and testing multiple pages for the project 4. Implmented configuration logic for integrating YouTube API to the project | 1. Faced issues when trying to query YouTube directly through flask | 1. Work on increasing the number of videos fetected through the app 2. Work on the video watching page 3. Work on capturing user's watching time and other meta data to gain insight on user's experience | 1. Design and write logic for the "Video watching" page where the user can play the video 2. Setup database and finalise database design to store user's watch history | 10
6 | 10/20-10/26 | 10 | 7 | 3 | 0 - Learn about YouTube Player API for tracking users watch time 5 - Conducted a session on react for the entire team 7 - Worked on migrating Youtube API call from front-end to back-end 7 - Designed Browsefeed section sperating YouTube videos in 3 sections as per duration | 1 |  |  |  | 2 |  |  | 4 | 1. Worked on migrating Youtube API call from front-end to back-end 2. Designing Browse Feed section for different video duration
7 | 10/27-11/02 | 9 | 7 | 2 | 5 - Conducted a session on cypress testcases 7 - Integrating YouTube player api with the code 7 - Tweaking YouTube API python api to support parameters requests with query, duration and total video count being passed as parameter 5 - Code reviewing teams pull requests | [5 empty] | 4 |  | 3 | 1. Refactoring YouTube API call into a single flask parameterized route to avoid duplicated code 2. Migrated from <iframe> to YouTube API Player which provides a more granular control over users action while watching videos | 1. npm issues while running teams changes locally for code review 2. multiple merge conflicts while dealing with merging teams code on git
8 | 11/03-11/09 | 15 | 11 | 4 | 7 - Integrating firestore database with the code 7 - Writing api's to add user details from user's google profile to firestore 7 - Writing api to read data from firestore to fetch users hobbies 7 - Integrating teams changes to the app 7 - Designing onboarding, see all videos and Youtube watch experience page 5 - Code review for teams changes 5 - Help team solve merge conflicts and other git related issues while merging | [5 empty] | 5 |  | 6 | 1. Integrated teams changes into the main app 2. Designed onboarding, see all videos and Youtube watch experience page 3. Integrated firestore and implemented read and write routes to update firestore | 1. Cypress test cases failing due to the login requirement 2. YouTube API exhausting total daily quota | 1. Started working on creating a spooler to pick different Youtube when one api is exhausted 2. Added failback to default user for cypress to work without login | 1. Write logic to write video related meta data to database and capture watch time 2. research for different web chart libraries to display analytics | 10
9 | 11/10-11/16 | 10 | 9 | 1 | 3 - Integrating firebase real-time database with the backend 2 - Designing Video Watching page with buttons for Like, Next, Previous and Close 3 - Implemented logic for Liking a video and saving the liked video details to the realtime database 3 - Implemented logic for playing the next or previous video |  |  | 1 | 8 |  |  |  |  | 1. Designed & Wrote logic for Video Watching Page |  |  | 1. Start working on tracking users watchtime | 5
10 | 11/17-11/23 | 9 | 8 | 1 | 0 - Researching how to get video player metadata for the duration of videos watched 3 - Wrote a dummy application to implement the logic to get users watchtime 3 - Integrating users watchtime logic with the Video Watching experience page 0 - Researching for Charts library to use for the analytics page | 4 |  |  | 4 |  |  |  |  | 1. Integrated the ability to track users watchtime while watching a youtube video |  |  | 1. Research Charting libraries that could be used for creating a Dashboard | 6
11 | 11/24-11/30 | 13 | 12 | 1 | 3 - Integrating Charts.js with the react app 3 - Implemented Bar chart to display first video clicks (short, medium, long) in Chart.js 3 - Implemented Donut Chart to display most used search keywords for both entertainment and education mode in Chart.JS 3 - Fixing issue with Chart.JS not being able to update graphs due to cache |  |  |  | 12 |  |  |  |  | 1. Implemented Analytics Dashboard with ChartJS | 1. Facing issues with ChartJS not being able to dynamically update graphs | 1. Decided to upgrade to ApexCharts | 1. Upgrade to ApexCharts for the dashboard | 5
12 | 12/01-12/10 | 28 | 8 | 20 | 3 - Updating charts usage from Chart.js with ApexCharts 3 - Updated Bar chart to display first video clicks (short, medium, long) using ApexCharts 3 - Updated Donut Chart to display most used search keywords for both entertainment and education mode using ApexCharts |  |  |  | 8 |  |  |  |  | 1. Implemented Analytics Dashboard with ApexCharts

## Sai Ramya
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project. |  | 1. Finalise a project idea. 2. work on risk mgmt doc
2 | 09/21-09/28 | 5 | 3 | 2 | 0 - learn github functions, brushing up Flask concepts 7 - Analyzed the risks for iteration 0 | 2 | [6 empty] | 1 | 1. completed the risk management document for the iteration 0
3 | 09/29-10/05 | 6 | 3 | 3 | 2 - discussing and creating user stories |  |  | 3
4 | 10/06-10/12 | 6 | 5 | 3 | 0 - learn flask 2 - drafted low level wireframes | 3 |  | 2 | [5 empty] | 1. Help with the low level wireframes for further user stories
5 | 10/13-10/19 | 6 | 4 | 4 | 0 - learn react, brush up flask 5 - discuss low wireframes | 2 |  |  |  |  | 3 |  |  | 1. Worked on the SDDD , database design
6 | 10/20-10/26 | 7 | 5 | 2 | 0 - learn react, understand the already existing code that has been built and try building reusable components. | 5 | [7 empty] | 1. Started implementing the Jira assigned to me SE-29
7 | 10/27-11/02 | 4 | 3 | 1 | 3 - trying implementation of reusable components to display on see more button from the education page |  |  |  | 3
8 | 11/03-11/11 | 17 | 11 | 6 | 3 - Implement the landing page for the see more videos. 7- Faced issues and pair programmed with siddhesh and deepali for PR's and issues within the assigned tasks. 7- Worked on documentation for the project. |  |  |  | 11 |  |  |  | 6 | 1. submitted PR for changes. 2. Worked on SDDD changes requested by Prof. after Iteration1. 3. Worked on STD documentation. | Issues faced with react, was facing difficulty in fetching states
9 | 11/12-11/20 | 5 | 4 | 1 | 4 - added cypress tests for frontend |  |  |  |  | 4
10 | 11/21-11/27 | 6 | 5 | 1 | 0 - Had to learn about Cypress tests in details to work on other features 0 - Had to learn about Unit tests to work on it in | 5
11 | 11/28-12/4 | 11 | 10 | 1 | 0 - Had to revisit few topics in React as needed for the task 3 - Video Watching Experience Buttons 3 - Pair programmed with Siddhesh to resolve Backend related issues 7 - Prepared presentation slides | 2 |  |  | 6 |  |  |  | 2 | 1. The Buttons under the video. 2. Slides for Presentation
12 | 12/4-12/10 | 40 | 20 | 20 | 4 - Tests - Cypress tests for Buttons 3 - Reverted few code changes which cause issues. 3 - Coded the connection from Firebase to Frontend for Video details fetch 4 - Tests - Unit Test for Wrapper 3 - Refactoring - EntertainmentFeed.js 3 - Fixed Bugs in Entertainment (Issue 31) 5 - Helped team members with PR and git commits 7 - Reviewing and merging PRs 7 - ReadME changes in Git |  |  |  | 5 | 10 | 3 |  | 2 | 1. Commited all the changes I made 2. Created PR 's for all the changes I worked on 3.Managed user stories on JIRA - assigning , changing status

## Supriya
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project.
2 | 09/21-09/28 | 4 | 2 | 2 | 0 - learn github functions,commands, learn Flask concepts,discussion with team lead regarding project learn deployment for flask and react | 2 | [7 empty] | 1. completed the document for the iteration 0
3 | 09/29-10/05 | 6 | 3 | 3 | 2. Discussing User Stories. |  |  | 2
4 | 10/06-10/12 | 12 | 8 | 3 | 0. Acquring proficiency in github actions Learn JIRA LEARN FLASK | 5 | [5 empty] | 3 |  | 1.assistance with low level wireframes for use cases
5 | 10/13-10/19 | 6 | 5 | 2 | 0.Gaining proficiency in GitHub tools and Flask 2. worked on user stories | 4 |  | 1
6 | 10/20-10/26 | 7 | 5 | 2 | 0.Understand how to use React and comprehend the built-in code currently there. | 6 | [7 empty] | began working on the Jira that was assigned to me, SE-34.
7 | 10/27-11/02 | 7 | 6 | 1 | 3. composed and created the user profile page's code 0.Learn the fundamentals of React and the current codeflow. | 1 |  |  | 5 |  |  |  |  | began working on the Jira that was assigned to me, SE-35.
8 | 11/03-11/09 | 19 | 17 | 2 | 3. Composed code to generate a webpage for viewing video history. 0.Engaged in learning React components and familiarizing o with Git commands 7.encountered problems and worked with Deepali to solve problems and PRs related to the tasks given. worked on the project's documentation. | 14 | [6 empty] | 3 | submitted PR for changes for SE-34 and SE-35
9 | 11/10-11/16 | 2 | 1 | 1 | 4. worked on cypress testing . |  |  |  |  | 2
10 | 11/17-11/23 | 2 | 1 | 1 | 3.working on user profile page 0 - learn youtube player api | 2 |  |  | 5
11 | 11/24-11/30 | 2 | 1 | 1 | 0. learn youtube player api | 1
12 | 12/01-12/10 | 41 | 21 | 20 | 3.worked on removing dead code. 3.worked on adding comments to pages. 4. worked on issues (git) 3. updated readme file 7.Reveiwing PR's |  |  |  | 25 | 8 |  |  | 1 | Submitted PR for changes for SE-70,SE-72,SE-50

## Deepali
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project. |  | 1. Finalise a project idea. 2. work on SPPP
2 | 09/21-09/28 | 10 | 8 | 2 | 0 - learn github actions, deployment for flask and react, docker containerisation 5 - decided on and discussed configuration plan and QA plan with team members 6 - came up with a configuration plan | 5 |  |  |  |  | 2 | 1 |  | 1. started process of configuration of CI/CD tools using github actions | 1. Not familiar with react 2. Not familiar with QA processes | 1. took help from team member for React. 2. learning more about QA metrics and testing. 3. plan: complete CI/CD configuration and try it out on a dummy application
3 | 09/29-10/05 | 7 | 4 | 3 | 2 - discussing and creating user stories |  |  | 4
4 | 10/06-10/12 | 12 | 9 | 3 | 0 - learn github actions 6 - tested configurations for different pre-existing action tools, imported user stories from pivotal tracker to JIRA, set up JIRA | 4 | [5 empty] | 5 |  | 1. set up the JIRA project, started sprint 2. tried out configuring automated tools on dummy app
5 | 10/13-10/19 | 14.5 | 10.5 | 4 | 0 - learn react, brush up flask 4 - tested configurations on project github repo - resolve errors 5 - discuss lofi wireframes | 3 |  |  |  | 7 | 0.5 |  |  | 1. set up github action tools on repo | 1. Issues faced with github action tools, several tools were incompatible, or required a paid subscription | 1. referred to documentations and resources online
6 | 10/20-10/26 | 7 | 5 | 2 | 0 - learn react, understand how it will be used in our project through Siddhesh's demo. 5 - prepare documentation for team members for github usage, PR standards etc. 6 - look at deployment options for the project | 3 |  |  |  |  | 1 | 1 |  | 1. documentation for git usage
7 | 10/27-11/02 | 4 | 3 | 1 | 0 - try basic react and understand existing codeflow | 3
8 | 11/03-11/09 | 19 | 18 | 1 | 0 - get familiarised with cypress 3 - Implement the landing page for the entertainment feed. 5 - helped teammates with git issues, reviewed PRs, and merged and tested code. | 1 |  |  | 10 |  | 7 |  |  | 1. submitted PR for changes | Issues faced with react, was stuck at component usage within loops
9 | 11/10-11/16 | 9 | 8 | 1 | 4 - added unit tests for backend, added cypress tests |  |  |  |  | 8 |  |  |  | 1. submitted PR for changes
10 | 11/17-11/23 | 5 | 4 | 1 | 0 - learn red hat open shift container deployment 7 - github session to entire team | 2 | [6 empty] | 2
11 | 11/24-11/30 | 8 | 7 | 1 | 0 - learn youtube player api 3 - reward points - read/write from database | 4 |  |  | 3
12 | 12/01-12/10 | 45 | 25 | 20 | 3 - reward points - add/deduct 5 - helping everyone with git commits/PRs/merge conflicts 6 - github action tester script update 7 - Reviewing and merging PRs |  |  |  | 8 |  | 12 | 1 | 4 | 1. submitted PR for changes

## Ayush
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project.
2 | 09/21-09/28 | 6 | 4 | 2 | 0 - Discover the various features and functionalities of GitHub including GitHub Desktop, Issues, and Pull Requests. 5 - Had group meetings and worked on the progress report and other documentation for Iteration 0. | 3 |  |  |  |  | 1 |  |  | 1. Discussed and worked on progress report.
3 | 09/29-10/05 | 5 | 3 | 2 | 2 - Discussed and create user stories |  |  | 3
4 | 10/06-10/13 | 5 | 2 | 3 | 0 - learn JIRA and flask 6 - tested configurations for different action tools | 1 | [5 empty] | 1 |  | 1.Worked on tasks from pivotal tracker
5 | 10/13-10/19 | 6 | 4 | 2 | 0- Learn flask and user stories 5 -Worked on progress report documentation. 6-Discussed and worked on abuse on use case for project | 1 |  |  |  |  | 1 | 2
6 | 10/20-10/26 | 4 | 2 | 2 | 0- Learn flask and react 5- talked about the different wireframes that will be needed | 1 |  |  |  |  | 1 |  |  | 1. Worked on progress report and final documentation.
7 | 10/27-11/02 | 4 | 3 | 1 | 1- learn about react and our codeflow 2- designed a wireframe for the onboarding page | 1 | 2 | [6 empty] | 1. Started with the tasked assigned in JIRA SE-38
8 | 11/03-11/10 | 12 | 8 | 4 | 0- learn react and its libraries 3- Implemented the onboarding page and also linked it with signup page with the help of pushkar. 5- discuss about issues to add code in git and also learn about JIRA user stories | 1 |  | 5 |  |  | 2 |  |  | 1. submitted PR for changes and made changes as asked. 2. Worked on progress report | Issues faced in git PR was not able to connect code with git and issues with fetching code.
9 | 11/10-11/16 | 3 | 2 | 1 | 0 - Learned about cypress testing 4 - worked on cypress testing 0 - Learned more about react |  |  |  |  | 2
10 | 11/17-11/23 | 2 | 1 | 1 | 0 - getting familiar with cypress api testing 3 - implemented session timer 1 - started implementing reward points | 1
11 | 11/24-11/30 | 6 | 5 | 1 | 0 -Learn about flask and api testing 3- worked on screen timer 3- worked on adding reward points | 1 |  |  | 4 | [5 empty] | 1.Had issues in making pull requests and pushing my data on github
12 | 12/01-12/10 | 32 | 12 | 20 | 0 - learning API testing 2 - Design new user profile page 3 - updated userprofile page 3 - worked on onboarding page 3 - Updated UI part 4 - worked on cypress API test | 2 |  |  |  | 8 |  |  | 2 | 1. Did testing on the different features included in the project 2. Made PRs for each one of them 3. Reviewed and merged PRs | 1. Faced many issues during testing. | 1. Took help from the members for testing some features and issues.

## Paridhi
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirements leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project.
2 | 09/21-09/28 | 9 | 7 | 2 | 0 - learn GitHub features and functionalities such as Github Desktop, brush on Flask and React, and learn about JIRA and Cypress. 5 - had meetings and worked on the progress report. | 4 |  |  |  |  | 3 |  |  | 1. completed the group progress report.
3 | 09/28-10/06 | 7 | 4 | 3 | 2 - Created user stories |  | 4
4 | 10/06-10/13 | 10 | 7 | 3 | 0 - learn Flask and React, and learn about JIRA and Cypress. 2 - edited and manually added user stories. | 5 | 2 | [6 empty] | 1. Completed editing and updating the user stories imported from pivotal tracker.
5 | 10/13-10/19 | 12 | 8 | 4 | 2 - created more user stories based on the wireframes. 5 - attended meetings and worked on documentation. Discussed the wireframes construction and gave suggestions. |  | 4 |  |  |  | 4 |  |  | 1. Completed working on the user stories. 2. Completed documentation. | Faced issues in exporting user stories in bulk from JIRA to Github and Drive.
6 | 10/20-10/26 | 4 | 2 | 2 | 0 - learn React and understand the basic structure of the existing code. | 2
7 | 10/27-11/02 | 4 | 3 | 1 | 0 - learn React and how to build the watch page. 2 - updated Jira stories as we started working on it. | 2 | 1
8 | 11/03-11/09 | 13 | 11 | 2 | 0 - learn about the TDD technique. 2 - updated Jira stories progress. 3 - started working on the implementation of watch page. 5 - faced issues in making pull requests, took help from team members. | 1 |  | 1 | 7 |  | 2 |  |  | 1. Completed implementation of the watch page. 2. Completed documentation. | 1. Faced issues in making pull requests and updating the final code(integration). 2. Faced issues in creating the watch page and usage of APIs. | 1. Took help from teammates for the github issues. 2. Referred to youtube videos to learn about the watch page and API usage.
9 | 11/10-11/16 | 3 | 2 | 1 | 4 - worked on cypress testing |  |  |  |  | 2
10 | 11/17-11/23 | 2 | 1 | 1 | 0 - getting familiar with cypress api testing | 1
11 | 11/24-11/30 | 6 | 5 | 1 | 0 - learning about the youtube player 3- worked on reward points system | 1 |  |  | 4
12 | 12/01-12/10 | 30 | 10 | 20 | 0 - learning more on cypress api testing 4 - worked on cypress API and UI tests 7 - reviewed and merged PRS | 2 |  |  |  | 8 |  |  | 2 | 1. Did testing on the different features included in the project 2. Made PRs for each one of them 3. Reviewed and merged PRs | 1. Faced many issues during testing. | 1. Took help from the members for testing some features and issues.

## Pushkar
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - Learn git commands and usage 6 - Set up git 7 - Discussed project ideas | 1 | [5 empty] | 1 | 2 | 1. Set up git 2. Shortlisted a few git tools and commands that would be useful for the project. |  |  | 1. Finish all the required documentations for Iteration 0 | 4
2 | 09/21-09/28 | 6 | 4 | 2 | 0 - Configured github. 5 - Had meetings and worked on the progress report. | 1 |  |  |  |  | 3 |  |  | 1. Worked on the groupreport and risk management report. |  |  | 1. Start implementing and work on basic of react. | 6
3 | 09/28-10/06 | 6 | 4 | 2 | 0- learn Pivotal tracker | 4 | [7 empty] | 1. Completed editing and updating the user stories imported from pivotal tracker.
4 | 10/06-10/13 | 5 | 2 | 3 | 4 - Examined the risks of project. 0- Learn flask and user stories 5 -Worked on risk management documentation. 6-Discussed and worked on abuse on use case for project |  |  | 2 | [5 empty] | 1. Completed the Designs patterns in SDD
5 | 10/13-10/19 | 6 | 5 | 1 | 2.Researched and designed the Design pattern. 3.Made the necessary adjustments in the risk management and carried out the required trials |  |  | 2 | 3 |  |  |  |  | 1. Work on the user stories was finished. 2. Finalized the documentation.
6 | 10/20-10/26 | 7 | 5 | 2 | 0 - learn react, followed project through Siddhesh's demo. 0 - learned from Deepali's documentation about github usage, PR standards etc. 1 - Started to research about authenticaiton system and Sign In functionality. | 3 | 2 | [6 empty] | 1. Started the implementing the Jira SE-25
7 | 10/27-11/02 | 4 | 3 | 1 | 3 - Completed the Jira SE-25 |  |  |  | 3 |  |  |  |  | 1. Solved the errors that occured during merging the code with the help of my fellow teammates | 1. Encountered some issues in the code while merging
8 | 11/03-11/09 | 10 | 6 | 4 | 0 - learnt more functionalities of Github 1 - Started to study about the Jira SE-32 3 - Helped Ayush with Onboarding page | 1 | 1 |  | 4 |  |  |  |  | 1. submitted PR for changes.
9 | 11/10-11/16 | 5 | 4 | 1 | 0 - Learned about cypress testing 4 - worked on cypress testing 0 - Learned more about react |  |  |  |  | 2
10 | 11/17-11/23 | 6 | 5 | 1 | 0 - getting familiar with cypress api testing 3 - implemented session timer 1 - started implementing reward points | 1
11 | 11/24-11/30 | 2 | 1 | 1 | 3 - implemented reward points | 1 |  |  | 4
12 | 12/01-12/10 | 34 | 12 | 22 | 3 - Improved styling and added animation in App 3 - Improved styling and added animation in Search 3 - Improved styling and added animation in Onboardingpage 3 - Improved Userprofilr.js 3 - Improved styling and added animation in Entertainment 3 - Improved styling and added animation in User profile 3 - Implmented cypress testing 3 - completed the documentation | 2 |  |  |  | 8 |  |  | 2 | 1. Did testing on the different features included in the project 2. Merged everychange in the main branch. | 1. Issues occured during test 2. Issues occured during styling | 1. Got some help of team members to complete the desired task