## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 09/14-09/21 | Finalised a project idea. Learned about some github features. Decided the roles of each member | Members faced few issues on the implementation of Lab1. Sought assistance from teammates. | Faced issues with deciding on the weekly meeting schedule. | Discussed the project idea with Professor. Added a few functionalities to our project based on Professor's suggestions. | [5 empty] | 6 | 26 | 1
0 | 09/21-09/28 | Discussed the configuration and QA plan. Finalized the tech stack. Analyzed the risks of the project. Analyzed performance metrics for the project. Worked on the documentation. Worked on the presentation for iteration 0. | Members are not familiar with certain frameworks. | None | - Switched from JIRA to Pivotal Tracker. - Decided to change our branching strategy from Git Flow to GitHub flow branching strategy. | [5 empty] | 10.5 | 36 | 2

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Siddhesh
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Team Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 7 | 6 | 1 | 5 - helping team members to onboard to git repository and help with their git repo setup, Communicating with team to find common time to schedule weekly meeting 6 - git repository creation, set up git repo locallly 7 - think and discuss project ideas | [5 empty] | 2 | 1 | 3 | 1. set up git 2. finalized tech stack to be used for the project |  | 1 - Finalise a project idea. 2 - work on SPPP 3 - Work on Presentation for iteration 0 | 1. Finish all the required documentations for Iteration 0 | 6
2 | 09/21-09/28 | 10 | 8 | 2 | 0 - learn about YouTube API, Integration of firebase with Python Flask 5 - deciding performance metrics, functional and non functional requirements & disscussing tools to use for CI/CD and Testing, Preparing presentation & SPPP Document with teammates for Iteration 0 | 3 |  |  |  |  | 5 |  |  | 1. started working on creating features/tasks to be made into JIRA tickets | 1. Not very familiar with integration between Flask and Firebase | 1. Learning about YouTube API and exploring its features by creating a dummy application 2. Learning about Firebase integration with Flask by creating a dummy application 3. Learn more about code review techniques and quality assurance metrics | 1. Write initial feature stories and find time to connect with team to groom feature stories and acceptance criteria 2. Work on initial wireframes / mockups with team members for core functionalities and screens 3. Setup a call with team members for teaching basics of React | 7

## Supriya
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project.
2 | 09/21-09/28 | 4 | 2 | 2 | 0 - learn github functions,commands, learn Flask concepts,discussion with team lead regarding project learn deployment for flask and react | 2 | [7 empty] | 1. completed the document for the iteration 0

## Sai Ramya
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project. |  | 1. Finalise a project idea. 2. work on risk mgmt doc
2 | 09/21-09/28 | 5 | 3 | 2 | 0 - learn github functions, brushing up Flask concepts 7 - Analyzed the risks for iteration 0 | 2 | [6 empty] | 1 | 1. completed the risk management document for the iteration 0

## Paridhi
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirements leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project.
2 | 09/21-09/28 | 9 | 7 | 2 | 0 - learn GitHub features and functionalities such as Github Desktop, brush on Flask and React, and learn about JIRA and Cypress. 5 - had meetings and worked on the progress report. | 4 |  |  |  |  | 3 |  |  | 1. completed the group progress report.

## Ayush
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project.
2 | 09/21-09/28 | 6 | 4 | 2 | 0 - Discover the various features and functionalities of GitHub including GitHub Desktop, Issues, and Pull Requests. 5 - Had group meetings and worked on the progress report and other documentation for Iteration 0. | 3 |  |  |  |  | 5 |  |  | 1. Discussed and worked on progress report.

## Deepali
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - learn git commands and usage 6 - set up git 7 - think and discuss project ideas | 1 | [5 empty] | 1 | 2 | 1. set up git 2. shortlisted a few git tools and commands that would be useful for the project. |  | 1. Finalise a project idea. 2. work on SPPP
2 | 09/21-09/28 | 10 | 8 | 2 | 0 - learn github actions, deployment for flask and react, docker containerisation 5 - decided on and discussed configuration plan and QA plan with team members 6 - came up with a configuration plan | 5 |  |  |  |  | 2 | 1 |  | 1. started process of configuration of CI/CD tools using github actions | 1. Not familiar with react 2. Not familiar with QA processes | 1. took help from team member for React. 2. learning more about QA metrics and testing. 3. plan: complete CI/CD configuration and try it out on a dummy application

## Pushkar
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Design and Implementation Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/14-09/21 | 5 | 4 | 1 | 0 - Learn git commands and usage 6 - Set up git 7 - Discussed project ideas | 1 | [5 empty] | 1 | 2 | 1. Set up git 2. Shortlisted a few git tools and commands that would be useful for the project. |  |  | 1. Finish all the required documentations for Iteration 0 | 4
2 | 09/21-09/28 | 6 | 4 | 2 | 0 - Configured github. 5 - Had meetings and worked on the progress report. | 1 |  |  |  |  | 3 |  |  | 1. Worked on the groupreport and risk management report. |  |  | 1. Start implementing and work on basic of react. | 6