## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | Loss team members | One or more team members drop the class | 1 | 5 | 4 | 20 | Team leader and all members | 2023-11-09 | Redefine the project scope if necessary, and assign the tasks to other team members. | No one has dropped the course from our team so far | Open
| add new team members | One or more new teammates are added to the team | 1 | 5 | 2 | 10 | Team leader and all members | 2023-09-25 | New member has been informed about the project idea and all the tasks that need to be done from her end | New Team member was onboarded to the team and is individually finishing LAB 1. This will be committed to the repo. | Closed
| Lack of motivation or responsibility | Lack of motivation can be caused due to commitment to other academic related work. | 3 | 4 | 1 | 12 | Team leader and all members | 2023-11-09 | We plan to use pair programming technique for majority of our work so that atleast 1 team member would be accountable in case the other one lacks motivation. We also plan to assign backup roles in case a team member can't finish his/her work due to other commitments. | N/A | Open
Communication | duplicate work | Multiple people working on similar logic in different components can cause duplicate work. | 4 | 2 | 1 | 8 | Team Leader | 2023-12-07 | We plan to make sure all the task assignments are done in the presence of all the team members so that everyone knowns the task in hand avoiding duplicate work | N/A | Open
| worked on wrong components | Due to human error someone can work on other teammamtes tickets. | 3 | 4 | 1 | 12 | Team leader and all members | 2023-12-07 | Regular status updates would help detect this issue earlier and in general would help mitigate it faster. | N/A | Open
| useless work | team focusing on unnecessary components or functionalities that are trivial. | 3 | 4 | 5 | 60 | Team Leader | 2023-11-09 | We plan to discuss and focus on finding features that have more priority and need to be completed sooner. These tasks would be given priority over other trivial tasks | N/A | Open
| inconsistent work | Team does not commit their code to github regularly/not rebasing their code before working on their tasks causing inconsistency. | 4 | 5 | 4 | 80 | Team leader and all members | 2023-12-07 | We would have regular reminders set to remind team members to commit regularly in case they forget because of their busy schedule | N/A | Open
Requirements | unclear requirements | feature stories are inconsistent or unclear. | 2 | 4 | 5 | 40 | Requirements Leader | 2023-11-09 | We plan to groom every story as part of a Story Grooming meeting where we go in detail about every feature story and its acceptance criteria. Story goes into implementation phase only if all the team members approve it. | N/A | Open
| scope creep | not focusing on the minimum viable products | 1 | 3 | 5 | 15 | Team Leader | 2023-11-09 | For the initial iteration we only plan to work on tickets that aim towards finishing the minimum viable product thus avoiding working on tickets that aren't part of it | N/A | Open
| constant requirements changes | Poor requirement analysis before implementation of any change. | 2 | 3 | 5 | 30 | Requirements Leader | 2023-11-09 | Before every iteration, we plan to have a sprint planning call where we go in detail about the requirements and its implementation in detail. | Every week a meeting is scheduled where tasks are assigned to the team memebers. | Open
Management | improper task assignments | Not focusing on the strengths of the members regarding technical knowledge while assigning tasks. | 2 | 4 | 4 | 32 | Team Leader | 2023-11-09 | While assigning tasks, every team member would have the option to pick tickets as per their liking. This makes sure that team members pick tasks that compliment their strong suite. | N/A | Open
| improper planning | unequal task distribution among the team members. | 4 | 2 | 4 | 32 | Team Leader | 2023-12-07 | Since we are planning to conduct sprint planning meetings before every iteration. It would help us identify the amount of task in every team memebers bucket. | N/A | Open
| lack of management skills | improper allocation of time required to complete a task. | 4 | 4 | 5 | 80 | Team Leader | 2023-12-07 | We would keep allocation time to minimum, If a task requires more than the max allocation time then we can divide the task into multiple subtasks rather spending a lot of time on a single task. | N/A | Open
Technology competence | Not familiar with the framework used | members sticking to their choice of framework lacking the ability to adapt to a new framework. | 3 | 2 | 2 | 12 | Team leader and all members | 2023-10-26 | All team members should make efforts to familiarise themselves with Flask and React, and reach out to other team members in case they need help in speeding up the learning process. | All team members are brushing up on concepts and getting doubts clarified related to Flask and React. | In Progress
| Not familiar with the programming language used | choosing a programming language that has a longer learning curve. | 3 | 3 | 3 | 27 | Configuration Leader | 2023-09-28 | We plan to keep learning sessions to help team members learn the required langugage faster. Pair programming would also help with this issue. | N/A | Open
| Not familiar with unit testing | writing incomplete unit tests or writing unit tests without proper understanding of the method. | 4 | 4 | 2 | 32 | QA Leader | 2023-12-07 | Every unit test would be reviewed and approved by the QA Leader before it is merged with any branch. | N/A | Open
| Other technology incompetence | members are not familiar with github action tools. | 4 | 3 | 3 | 36 | Configuration Leader | 2023-10-19 | Configuration leader would be responsible that all the team members understand how github action tools work | The utilization of github has been refined, all members are utilizing it, and they are all familiar with the instructions. Each member is using github to contribute to and integrate their portion of the project. | In Progress
| Not familiar with Git | accidentally hampering commits made by other team members due to a lack of familiarity with git | 3 | 3 | 2 | 18 | Team leader and all members | 2023-12-07 | All team members should make efforts to familiarise themselves with git, and reach out to other team members in case they need help in speeding up the learning process. | All team members are brushing up on concepts and getting doubts clarified related to Git. | In Progress
Design and implementation | Improper design | improper design could cause performance or scaling issues in the future. | 2 | 4 | 5 | 40 | Design and Implementation Leader | 2023-10-19 | We would monitor performance and scalling of the application every release to make sure it doesn't have any issues. | Trials are been conducted to make sure it passed every test and does not has any issues or error. | Open
| improper technology stack | Not properly researching the integration process for different elements in the tech stack | 2 | 2 | 4 | 16 | Design and Implementation Leader | 2023-10-19 | We would perform research to make sure that the choosen tech stack can be integrated properly | Conducted the research and choosen tech stack in being intergrated properly. | Open
| Messy code | Different team members use different coding standards. | 4 | 4 | 4 | 64 | Team leader and all members | 2023-11-09 | Proper communication, PRs that do not follow decided-upon coding standards will not be approved. | N/A | Open
Testing | Not enough testing | Some features were not tested while being pushed to github | 3 | 5 | 5 | 75 | QA Leader | 2023-12-07 | QA leader and Code reviewer would be responsilbe for making sure that tests are being performed before the code is pushed to github | N/A | Open
Integration and deployment | Not enough time for integration and deployment | Leaving integration and deployment for the end instead of doing so incrementally | 4 | 4 | 5 | 80 | QA Leader, Security Leader | 2023-12-07 | QA leader would be responsilbe for making sure that integration tests are being added with every new feature | N/A | Open